## Sheet1
Tutorial 1 | start date | start time | finish time | interuption or break duraction | calculated duration (hrs) | Description
first section of coding | 2020-10-13 | 10:35 | 11:00 | 0:11 | 0:14 | Only a short section of coding was needed for this reason why it didn’t take very long
Test the cube | 2020-10-13 | 11:00 | 13:00 | 0:20 | 1:40 | Code want working properly so had to go back into visual studios to check for any errors which didn't work meaning I had to look on forms to see if anyone had a solution for my issue
second section of coding | 2020-10-13 | 14:00 | 15:00 | 0:00 | 1:00 | A short section of code just copying and pasting past codes which is why the time it didn’t take so long
second cube test | 2020-10-13 | 15:00 | 16:00 | 0:30 | 0:30 | Didn’t get many errors in my test and if so was very simple to fix
Write out tutorial | 2020-10-13 | 16:00 | 19:30 | 1:00 | 2:30 | Using screenshots I grabbed through this prosses to create my step by step tutorial had to write about each screenshot with deatil to give the person reading full understanding
Total |  |  |  | 2:01 | 5:54
Total (break - duration ) | 3:53
Tutorial 2 | start date | start time | finish time | interuption or break duraction | calculated duration (hrs) | Description
creating assets | 2020-10-20 | 10:20 | 10:25 | 0:00 | 0:05 | Created the assets to code on
first section of coding | 2020-10-20 | 10:25 | 11:25 | 0:00 | 1:00 | Created the code for first asset (The character)
testing code | 2020-10-20 | 11:25 | 11:46 | 0:05 | 0:16 | test to see if the code was working
second section of code | 2020-10-23 | 16:00 | 17:30 | 0:30 | 1:00 | Created code for camera
error appeared | 2020-10-23 | 17:30 | 18:55 | 1:00 | 0:25 | error appeared and began looking in forms and videos for the anwser
second section of code | 2020-10-23 | 20:20 | 21:00 | 0:00 | 0:40 | found the anwser and went straight back to coding
test code | 2020-10-23 | 21:00 | 21:05 | 0:00 | 0:05 | started to test the code to see if working
write tutorial | 2020-10-23 | 22:00 | 23:30 | 0:00 | 1:30 | began writing out a turoial step by step
total |  |  |  | 1:35 | 5:01
Total (break - duration ) | 3:26
Tutorial 3 | start date | start time | finish time | interuption or break duraction | calculated duration (hrs) | Description
Start code | 2020-10-27 | 10:00 | 16:00 | 1:00 | 5:00 | starting the code for making the Ai
Error in code | 2020-10-27 | 16:00 | 16:50 | 0:00 | 0:50 | error found in the code look through videos and forums to find the solution
Write tutorial | 2020-10-27 | 16:50 | 17:50 | 0:00 | 1:00 | write the steps that I did today
Continue coding | 2020-10-28 | 13:00 | 17:00 | 2:00 | 2:00 | coing the rest of the script found an error at 5 pm
Error in code | 2020-10-28 | 17:00 | 17:30 | 0:00 | 0:30 | error found was a simple fix and something I have had an issue with in the past
Write tutorial | 2020-10-28 | 17:30 | 18:30 | 0:00 | 1:00 | write the steps that I did today
Continue coding | 2020-10-30 | 12:00 | 14:00 | 0:00 | 2:00 | finish off where I left off
Error in code | 2020-10-30 | 14:00 | 20:00 | 3:00 | 3:00 | another error in the attacking section of my code
Write tutorial | 2020-10-30 | 20:00 | 21:00 | 0:00 | 1:00 | write the steps that I did today
Create game objects | 2020-10-02 | 10:00 | 10:09 | 0:00 | 0:09 | creating game objects for the codes to work on
Create nav mesh | 2020-10-02 | 10:10 | 10:30 | 0:00 | 0:20 | creating a navagation mesh so object know where they can travel
Error in mesh | 2020-10-02 | 10:30 | 11:39 | 0:00 | 1:09 | mesh wasn’t working propley so had to find a way to get them to work by looking at video forums and help from tutors
Test game | 2020-10-02 | 11:40 | 11:41 | 0:00 | 0:01 | test the game and it work first time
Write tutorial | 2020-10-02 | 12:00 | 12:50 | 0:05 | 0:45 | write the steps that I did today
total |  |  |  | 3:05 | 18:44
total (break - duration) | 15:39
Tutorial 4 | start date | start time | finish time | interuption or break duraction | calculated duration (hrs) | Description
Beginning coding | 2020-11-03 | 12:30 | 16:00 | 1:00 | 2:30 | working on the code that will allow the gun to fire
finishing off the code | 2020-11-03 | 16:00 | 17:40 | 0:30 | 1:10 | finished of the cde for the gun including the muzzle flahing and the positioning of bullets and where they would fly out of
write up tutorial | 2020-11-03 | 17:40 | 18:40 | 0:00 | 1:00 | write up the steps I got done today
creating the obejcts | 2020-11-04 | 12:00 | 12:05 | 0:00 | 0:05 | create objects and adjust them to how I want them
add script to object | 2020-11-04 | 12:05 | 13:05 | 0:00 | 1:00 | add the script adjusting it to my needs and then testing the script was a error part way through but sorted it
test whole game | 2020-11-04 | 13:10 | 13:40 | 0:00 | 0:30 | testing to see if it works correctly
write up tutorial | 2020-11-04 | 14:00 | 15:00 | 0:00 | 1:00 | finishing off tutorial
total |  |  |  | 1:30 | 7:15
total (break - duration) | 5:45
overall time for each tutorial | 28:43
My project | start date | start time | finish time | interuption or break duraction | calculated duration (hrs) | Description
creating main menu panel | 2020-11-10 | 10:00 | 10:30 | 0:00 | 0:30 | started adding the things I needed for the main menu
create buttons for menu | 2020-11-10 | 10:30 | 11:40 | 0:10 | 1:00 | creating the buttins for the menu for example the text and the button and making them work together
make buttons interactive | 2020-11-10 | 11:40 | 12:40 | 0:00 | 1:00 | Making it so you can press on the buttons and see that you are pressing on them
create options menu panel | 2020-11-10 | 12:40 | 13:00 | 0:00 | 0:20 | then made a game object for me to put the option buttons in
copy buttons across | 2020-11-10 | 13:00 | 13:05 | 0:00 | 0:05 | created the buttons and moved them into the game object
create volume slider | 2020-11-10 | 13:05 | 13:10 | 0:00 | 0:05 | create volume button for options menu
write up what I did so far | 2020-11-10 | 13:30 | 15:00 | 0:30 | 1:00 | wrote up part of my tutorial
started creating the code | 2020-11-17 | 10:00 | 12:00 | 0:30 | 1:30 | created the code for both the option and main menu
setting up code to menu | 2020-11-17 | 12:00 | 12:30 | 0:00 | 0:30 | adding the code to the menu and setting up each button
creating new scene for game | 2020-11-17 | 12:30 | 12:35 | 0:00 | 0:05 | creating the game menu to show your play button is working
teasting game | 2020-11-17 | 12:35 | 13:00 | 0:00 | 0:25 | test to see if all of the buttons are working properly
write up what I did so far | 2020-11-17 | 13:00 | 14:00 | 0:00 | 1:00 | wrote up part of my tutorial
Create volume slider | 2020-11-24 | 10:00 | 10:15 | 0:00 | 0:15 | created the slider for the volume to how I want it
Create the music | 2020-11-24 | 10:15 | 10:20 | 0:00 | 0:05 | created music in logic for an example of how the slider will turn it down
Create code for slider | 2020-11-24 | 10:20 | 12:25 | 0:30 | 1:35 | created the code for the slider
set up code | 2020-11-24 | 13:00 | 13:30 | 0:00 | 0:30 | set it up so it would work when I played it
test code | 2020-11-24 | 13:30 | 13:35 | 0:00 | 0:05 | test all of the game to see if everything is working together
fix error | 2020-11-24 | 13:40 | 14:00 | 0:00 | 0:20 | fixed the errors I had
gather screenshots | 2020-11-24 | 14:00 | 15:00 | 0:00 | 1:00 | gather all my screenshots for mu tutorial.